## DEPEDSEF 2026
Republic of the Philippines
Province of Cavite
MUNICIPALITY OF MAGALLANES
OFFICE OF THE MUNICIPAL ENGINEER
PROGRAM OF WORKS STATUS SUMMARY F.Y. 2025 - SEF FUNDED PROJECTS
2025-12-04
Item | Request Received Date | SCHOOL LEVEL | Project Location | Source of Fund | Status | Remarks / Comments | Last Modified Date | Project Title | Project Amount | POW | Project Type | Type of Construction
1 | 2025-12-04 | Elementary | Bendita 1 | SEF - 2026 | For Site Inspection |  | 2025-12-04 | REPAIR & IMPROVEMENT OF SCHOOL ENTRANCE & SCHOOL STAGE | 118200 |  | VERTICAL STRUCTURES | IMPROVEMENT
2 | 2025-12-04 | Elementary | Urdaneta | SEF - 2026 | For Site Inspection |  | 2025-12-04 | STAGE ENHANCEMENT AND DEVELOPMENT / ENTRANCE GATE IMPROVEMENT | 134000 |  | VERTICAL STRUCTURES | IMPROVEMENT
3 | 2025-12-04 | Elementary | Kabulusan | SEF - 2026 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY UNDER 100K | 2025-12-04 | INSTALLATION OF CANOPY PATHWAYS | 46500 |  | VERTICAL STRUCTURES | NEW
4 | 2025-12-04 | Elementary | Caluangan | SEF - 2026 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY UNDER 100K | 2025-12-04 | REPAIR OF CEILING OF PRINCIPALS OFFICE | 51300 |  | VERTICAL STRUCTURES | REPAIR / REHAB
5 | 2025-12-04 | Elementary | Magallanes (Pob. 1) | SEF - 2026 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY UNDER 100K | 2025-12-04 | CONCRETING OF PAVEMENT IN FRONT OF NEW BUILDING | 99000 |  | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
6 | 2025-12-04 | Elementary | Medina | SEF - 2026 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY UNDER 100K | 2025-12-04 | CONSTRUCTION PLANT BOXES AS SAFETY BARRIERS ALONG OPEN PAVEMENT | 48600 |  | ENVIRONMENT / DRRM | NEW
7 | 2025-12-04 | Elementary | Pacheco | SEF - 2026 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY UNDER 100K | 2025-12-04 | REPAIR AND INSTALLATION OF SCHOOL GATE RESURFACING OF THE ENTRANCE PATHWAY, TILING AND IMPROVEMENT OF STAGE | 98700 |  | VERTICAL STRUCTURES | REPAIR / REHAB
8 | 2025-12-04 | Elementary | Ramirez | SEF - 2026 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY UNDER 100K | 2025-12-04 | EXTENSION KITCHEN FOR THE SCHOOL CANTEEN | 70500 |  | VERTICAL STRUCTURES | IMPROVEMENT
9 | 2025-12-04 | Elementary | Tua | SEF - 2026 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY UNDER 100K | 2025-12-04 |  | 90000
10 | 2025-12-04 | Elementary | Magallanes (Pob. 1) | SEF - 2026 | For Site Inspection |  | 2025-12-04 | RENOVATION OF ROOFING, CEILING AND ELECTRICAL WIRINGS OF ADMINISTRATIVE BUILDING | 150000 |  | VERTICAL STRUCTURES | REPAIR / REHAB
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
Formulas:
Last Modified Date = [Last Modified Date, row above]

## LFP LGU 2025
Republic of the Philippines
Province of Cavite
MUNICIPALITY OF MAGALLANES
OFFICE OF THE MUNICIPAL ENGINEER
INFRASTRUCTURE PROJECT MONITORING SUMMARY F.Y. 2025 - LOCALLY FUNDED PROJECTS & MUNICIPAL FUNDED PROJECTS
2025-12-04
Item | Source of Fund | Sector | Project Title | Brief Description | Project Amount | Contract Amount | POW # | Project Location | Status |  |  |  | Technical Information |  |  |  |  | Last Modified Date | Project Type | Type of Construction
[12 empty] | NO. OF CALENDAR DAYS | IMPLEMENTATION PHASE
[9 empty] | Construction | Physical (%) | Payment |  | BIDDING DATE | NOA | NTP | TARGET COMP. | COC
INFRASTRUCTURE PROJECTS
1 | SAFPB 2024 | ECONIMIC DEVELOPMENT | UPGRADING OF LEVELS OF SERVICES & EXPANSION OF LEVEL III WATER SYSTEM | 2,570LM - PIPELAYING OF 100MMø UPVC PIPE | 13333333 | 13333333 | 019 S.2024 | Kabulusan | Completed | 100 | By Contractor - For Submission of Completed Docs | 310 |  |  | 2024-10-24 | 2025-08-30 | 2025-10-10 | 2025-12-04 | WATER SUPPLY & SANITATION | IMPROVEMENT
2 | LOAN | ECONIMIC DEVELOPMENT | UPGRADING, REHABILITATION, CONSTRUCTION, OPTIMIZATION AND IMPROVEMENT OF MAGALLANES WATER SUPPLY SYSTEM (LEVEL III) | 7,150 lm - Rehabilitation of Piping (Poblacion, Urdaneta, San Agustin); 1 Unit Elevated Water Tank; 2 Sets - Well Drilling; 2 Sets - Intelligent Supply | 89512209.38 | 89512209.38 | 001 S.2024 | Various Brgy. | On-going Implementation | 48 | By Contractor - For Submission of Completed Docs | 547 |  |  | 2024-12-02 | 2026-06-02 |  | 2025-12-04 | WATER SUPPLY & SANITATION | IMPROVEMENT
3 | SGLG-IF 2024 | ECONIMIC DEVELOPMENT | MALUSOG NA NANAY TUNGO SA MALIGAYANG BUHAY: PURCHASE OF EQUIPMENT FOR MAGALLANES BIRTHING OR LYING-IN CLINIC |  | 1153000 | 1153000 | - | Kabulusan | Completed | 100 | For Payment - Accounting Review | 90 |  |  | JUL 7 2025 | 2025-10-05 | 2025-10-05 | 2025-12-04 | HEALTH | IMPROVEMENT
4 | 20% D.F. | ECONIMIC DEVELOPMENT | COMPLETION OF PASALUBONG CENTER AT PUBLIC MARKET, BRGY. SAN AGUSTIN | Various Finishes | 1000000 | 999197.12 | 016 | San Agustin | Completed | 100 | For Payment - Accounting Review | 70 | 2025-08-20 | 2025-08-21 | 2025-09-03 | 2025-11-11 | 2025-10-20 | 2025-12-04 | ECONOMIC / AGRICULTURE | IMPROVEMENT
5 | 20% D.F. | ECONIMIC DEVELOPMENT | CONCRETING OF ROAD AT MALIGAYA ST., BRGY. TUA | 100 lm x 3.0 W x 0.15m thk - PCCP Road (Unreinforced) (USING ONE BAGGER MIXER) | 500000 | 449600 | 038 | Tua | Completed | 100 | For Approval of Completed Docs | 40 | 2025-09-11 | 2025-09-12 | 2025-09-26 | 2025-11-04 |  | 2025-12-04 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
6 | 20% D.F. | ECONIMIC DEVELOPMENT | IMPROVEMENT OF PUBLIC MARKET, BRGY. SAN AGUSTIN | Various Finishes, Public Market Marker, Canal Lining, Rehabilitation of Waste Water Line, etc. | 2000000 | 1676480.27 | 015a | San Agustin | On-going Implementation | 72 |  | 77 | 2025-09-18 | 2025-09-19 | 2025-09-29 | 2025-12-14 |  | 2025-12-04 | VERTICAL STRUCTURES | IMPROVEMENT
7 | 20% D.F. | ECONIMIC DEVELOPMENT | CONCRETING OF MANGGAHAN ROAD AT BRGY. RAMIREZ | 62.5 lm x 4.0 W x 0.2m thk - PCCP Road (Unreinforced) (USING ONE BAGGER MIXER) | 500000 | 424985.18 | 036a | Ramirez | Completed | 100 | Pending - For Completion of Documents | 45 | 2025-09-18 | 2025-09-19 | 2025-09-29 | 2025-11-12 | 2025-10-21 | 2025-12-04 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
8 | 20% D.F. | ECONIMIC DEVELOPMENT | CONCRETING OF KALYE BICOLAN ROAD , BRGY. BENDITA I | 93.33 lm x 3.0 W x 0.15m thk - PCCP Road (Unreinforced) (USING ONE BAGGER MIXER) | 500000 | 414245 | 048 | Bendita 1 | Completed | 100 | For Payment - Accounting Review | 45 | 2025-09-18 | 2025-09-19 | 2025-09-29 | 2025-11-12 | 2025-10-30 | 2025-12-04 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
9 | 20% D.F. | ECONIMIC DEVELOPMENT | CONCRETING OF MANGGAHAN ROAD AT BRGY. V | 42 lm x 5.0 W x 0.2m thk - PCCP Road (Unreinforced) with Concrete Demolition (USING ONE BAGGER MIXER) | 500000 | 410388.69 | 035a | Poblacion 5 | Completed | 100 | By Contractor - For Submission of Completed Docs | 50 | 2025-09-18 | 2025-09-19 | 2025-09-29 | 2025-11-17 |  | 2025-12-04 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | REPAIR / REHAB
10 | 20% D.F. | SOCIAL DEVELOPMENT | CONSTRUCTION OF CONCRETE BLEACHERS IN PLAZA COVERED COURT, BRGY. III | 59.2 LM - CONCRETE BLEACHERS; 3 SETS - VETERANS LOGO INSTALLATION; 2 SETS - VOLLEY BALL POLE GROUND INSERT; 8 SETS - REPAIR & REHABILITATION OF 8 SETS STEEL COLUMN IN STAGE AREA | 1624584.4 | 1299668 | 049 | San Agustin | On-going Implementation | 58 |  | 75 | 2025-10-02 | 2025-10-03 | 2025-10-13 | 2025-12-26 |  | 2025-12-04 | ECONOMIC / AGRICULTURE | IMPROVEMENT
11 | 20% D.F. | SOCIAL DEVELOPMENT | CONSTRUCTION OF MULTIPURPOSE BUILDING IN PLAZA/COVERED COURT, BRGY. III | 181.7 SQM - MULTIPURPOSE BUILDING (TWO (2) UNITS MULTIPURPOSE ROOMS W/ ONE (1) UNIT TOILET; THREE (3) UNITS COMMON TOILET (PWD, MALE , FEMALE); TWO (2) UNITS BRGY. III TOILET (MALE , FEMALE); ONE (1) UNIT UTILITY / MAINTENANCE STORAGE ROOM) | 4526202 | 3797244.5 | 050 | Poblacion 3 | On-going Implementation | 42 |  | 75 | 2025-10-02 | 2025-10-03 | 2025-10-13 | 2025-12-26 |  | 2025-12-04 | VERTICAL STRUCTURES | IMPROVEMENT
12 | 20% D.F. | SOCIAL DEVELOPMENT | UPGRADING OF ANIMAL IMPOUNDING FACILITY AT SITIO KAYHABOL | 170 SQM - IMPOUNDING FACILITY; 5 SETS - 1.0 W X 1.0 H X 3.0M L) PET HOUSE STEEL FRAME | 1000000 | 833274.75 | 051 | Ramirez | On-going Implementation | 11 |  | 75 | 2025-10-07 | 2025-10-08 | 2025-10-14 | 2025-12-27 |  | 2025-12-04 | VERTICAL STRUCTURES | NEW
13 | 20% D.F. | SOCIAL DEVELOPMENT | INSTALLATION OF SOLAR STREET LIGHTS AT PUROK 4, BRGY. CALUANGAN | 11 SETS SOLAR STREET LIGHTS WITH POST | 575000 | 564801.86 | 052 | Caluangan | On-going Implementation | 68.75 |  | 55 | 2025-10-03 | 2025-10-06 | 2025-10-14 | 2025-12-07 |  | 2025-12-04 | TELECOMMUNICATION / POWER & LIGHT SERVICE | NEW
14 | 20% D.F. | SOCIAL DEVELOPMENT | INSTALLATION OF SOLAR STREET LIGHTS AT SITIO SUMANDAL, BRGY. KABULUSAN | 11 SETS SOLAR STREET LIGHTS WITH POST | 575000 | 564801.86 | 053 | Kabulusan | On-going Implementation | 68.75 |  | 55 | 2025-10-03 | 2025-10-06 | 2025-10-14 | 2025-12-07 |  | 2025-12-04 | TELECOMMUNICATION / POWER & LIGHT SERVICE | NEW
15 | 20% D.F. | SOCIAL DEVELOPMENT | INSTALLATION OF SOLAR STREET LIGHTS AT BRGY. URDANETA PROPER | 11 SETS SOLAR STREET LIGHTS WITH POST | 575000 | 509730.64 | 054 | Urdaneta | On-going Implementation | 68.75 |  | 55 | 2025-10-03 | 2025-10-06 | 2025-10-14 | 2025-12-07 |  | 2025-12-04 | TELECOMMUNICATION / POWER & LIGHT SERVICE | NEW
16 | 20% D.F. | ECONIMIC DEVELOPMENT | CONCRETING OF ROAD AT SITIO KAY-IMUS 2, KAY-APAS, BRGY. MEDINA | 52 lm x 6.0 W x 0.15m thk - PCCP Road (USING RMC) | 575000 | 455983 | 055 | Medina | On-going Implementation | 100 |  | 60 | 2025-10-07 | 2025-10-08 | 2025-10-14 | 2025-12-12 |  | 2025-12-04 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
17 | 20% D.F. | ECONIMIC DEVELOPMENT | CONCRETING OF ROAD AT VILLA LUDY, BRGY. BENDITA II | 86 lm x 4.0 W x 0.15m thk - PCCP Road (USING ONE BAGGER) | 575000 | 460000 | 056 | Bendita 2 | On-going Implementation | 71 | Pending - For Completion of Documents | 60 | 2025-10-07 | 2025-10-08 | 2025-10-14 | 2025-12-12 |  | 2025-12-04 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
18 | 20% D.F. | ENVIRONMENTAL MANAGEMENT | RIPRAPING AT SALCEDO STREET, NEAR MAES, BRGY. 2-POBLACION | 47 LM - (93.77 CUM - GROUTED RIPRAP VOLUME) | 575000 | 460022 | 057 | Poblacion 2 | Completed | 100 | Pending - For Completion of Documents | 60 | 2025-10-03 | 2025-10-06 | 2025-10-14 | 2025-12-12 |  | 2025-12-04 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
19 | 20% D.F. | ENVIRONMENTAL MANAGEMENT | CANAL LINING OF COLON STREET EXTENSION, BRGY 1-POBLACION | 220.8 LM - CANAL LINING | 575000 | 558247.85 | 058 | Poblacion 1 | Completed | 100 | By Contractor - For Submission of Completed Docs | 60 | 2025-10-03 | 2025-10-06 | 2025-10-14 | 2025-12-12 |  | 2025-12-04 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | IMPROVEMENT
20 | 20% D.F. | ENVIRONMENTAL MANAGEMENT | RECONSTRUCTION OF CANAL AT JOVILLAR, DE GUIA AND SALCEDO ST., BRGY 3-POBLACION | 268.4 LM - CANAL COVER (RECONSTRUCTION & NEW CONCSTRUCTION) | 575000 | 517217.79 | 059 | Poblacion 3 | On-going Implementation | 82 |  | 60 | 2025-10-07 | 2025-10-08 | 2025-10-14 | 2025-12-12 |  | 2025-12-04 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | REPAIR / REHAB
21 | 20% D.F. | ENVIRONMENTAL MANAGEMENT | COVERING OF CANAL AT JOVILLAR STREET, BARNGAY 4-POBLACION | 291.9 LM - CANAL COVER (RECONSTRUCTION & NEW CONCSTRUCTION) | 575000 | 545327.74 | 060 | Poblacion 4 | On-going Implementation | 41 |  | 60 | OCT 8 2025 | 2025-10-09 | 2025-10-15 | 2025-12-13 |  | 2025-12-04 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | IMPROVEMENT
22 | 20% D.F. | SOCIAL DEVELOPMENT | IMPROVEMENT OF COVERED COURT AT BRGY. SAN AGUSTIN | 67 LM - COVERED COURT FENCING | 575000 | 459226.66 | 061 | San Agustin | On-going Implementation | 30 |  | 60 | OCT 10 2025 |  | 2025-10-16 | 2025-12-14 |  | 2025-12-04 | VERTICAL STRUCTURES | IMPROVEMENT
23 | 20% D.F. | SOCIAL DEVELOPMENT | ADDITIONAL CONSTRUCTION OF SECOND FLOOR AT PACHECO MULTI-PURPOSE BUILDING | 36 SQM - PROVISION FOR COVERED 2ND FLOOR INCLUDING VARIOUS FINISHES | 575000 |  | 062 | Pacheco | On-going Implementation | 22 |  | 60 | OCT 16 2025 |  |  | 2025-12-22 |  | 2025-12-04 | VERTICAL STRUCTURES | IMPROVEMENT
24 | 20% D.F. | SOCIAL DEVELOPMENT | IMPROVEMENT (EXPANSION) OF MULTI-PURPOSE BUILDING OF BARANGAY BALIWAG | 10.3 LM - PERIMETER FENCE; 93.38 SQM - ROOFING WORKS; CONCRETE FLOORING - 82.4 SQM; 14.7 LM - DRAINAGE W/ STEEL COVER | 575000 | 450769.01 | 063 | Baliwag | On-going Implementation | 17 |  | 60 | OCT 10 2025 | 2025-10-13 | 2025-10-16 | 2025-12-14 |  | 2025-12-04 | VERTICAL STRUCTURES | IMPROVEMENT
1 | SEF 2025 | OTHERS | IMPROVEMENT / REHABILITATION OF FOUR (4) STOREY SCHOOLS IN BENDITA INTEGRATED HIGH SCHOOL | Roofing & Ceiling Works Repair; Plumbing Sanitary Works; Doors | 260100 | 256976.31 | 017a | Bendita 2 | Completed | 100 | Pending - For Completion of Documents | 40 | SEPT 9 2025 | Sept 10, 2025 | Sept 26, 2025 | 2025-11-05 | 2025-10-13 | 2025-12-04 | VERTICAL STRUCTURES | IMPROVEMENT
NON-INFRASTRUCTURE PROJECTS
1 | 20% D.F. | ECONIMIC DEVELOPMENT | PURCHASE OF WATER TANKER |  | 2800000 | [12 empty] | 2025-12-04
2 | 20% D.F. | ENVIRONMENTAL MANAGEMENT | PURCHASE OF GARBAGE COMPACTOR TRUCK |  | 5600000 | [7 empty] | SEPT 11 2025 |  |  |  |  | 2025-12-04
3 | 20% D.F. | SOCIAL DEVELOPMENT | LOAN AMORTIXATION RE: REHAB./IMPROVEMENT OF WATER SYSTEM AND PURCHASE OF LOT AT MAANGYO |  | 1700000 | [12 empty] | 2025-12-04
Formulas:
Last Modified Date = [Last Modified Date, row below]
Last Modified Date = [Last Modified Date, row above]

## BARANGAY 2025
Republic of the Philippines
Province of Cavite
MUNICIPALITY OF MAGALLANES
OFFICE OF THE MUNICIPAL ENGINEER
PROGRAM OF WORKS STATUS SUMMARY F.Y. 2025 - BARANGAY FUND (20% D.F.)
[5 empty] | - | 2025-12-04
Item | Request Received Date | Project Location | Source of Fund | Status | Remarks / Comments | Last Modified Date | Project Title | Project Amount | POW # | Project Type | Type of Construction
1 | 2025-02-03 | San Agustin | Brgy - 20% DF | Released | Received Feb 24, 2025 | 2025-12-04 | IMPROVEMENT OF MULTIPURPOSE HALL (CCTV INSTALLATION), BRGY. SAN AGUSTIN | 300000 | 003 | ENVIRONMENT / DRRM | NEW
2 | 2025-02-03 | San Agustin | Brgy - 20% DF | Released | Received Feb 24, 2025 | 2025-12-04 | CONSTRUCTION OF CREEK RETAINING WALL IN KINAANURAN CREEK, BRGY. SAN AGUSTIN | 116053 | 001 | VERTICAL STRUCTURES | NEW
3 | 2025-02-03 | Pacheco | Brgy - 20% DF | Released | Received Feb 24, 2025 | 2025-12-04 | INSTALLATION OF SOLAR LIGHTS IN BRGY. PACHECO | 300000 | 002 | TELECOMMUNICATION / POWER & LIGHT SERVICE | NEW
4 | 2025-02-13 | Poblacion 1 | Brgy - 20% DF | Released | Received Mar 12, 2025 | 2025-12-04 | CONCRETING OF BARANGAY ROAD AT COLON ST. EXTENSION | 210000 | 005 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
5 | 2025-02-13 | Poblacion 1 | Brgy - 20% DF | Released | Received Mar 12, 2025 | 2025-12-04 | CONCRETING OF BARANGAY ROAD AT DE GUIA ST. EXTENSION (A) | 70000 | 004 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
6 | 2025-02-13 | Poblacion 1 | Brgy - 20% DF | Released | Received Mar 12, 2025 | 2025-12-04 | CONSTRUCTION OF CANAL LINING AT REAL ST. EXTENSION | 122000 | 006 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
7 | 2025-02-27 | Ramirez | Brgy - 20% DF | Released | Received Mar 12, 2025 | 2025-12-04 | INSTALLATION OF SOLAR STREET LIGHTS WITH PANEL IN SITIO IMBURNAL, BRGY. RAMIREZ | 206202.6 | 007 | TELECOMMUNICATION / POWER & LIGHT SERVICE | NEW
8 | 2025-03-12 | Bendita 2 | Brgy - 20% DF | Released | Received Mar 27, 2025 | 2025-12-04 | CONCRETING OF PATHWALK IN SITIO NAGLAYON, BRGY. BENDITA II | 49500 | 012 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
9 | 2025-05-19 | Bendita 2 | Brgy - 20% DF | Released | POW RELEASED DATE: JULY 21, 2025 | 2025-12-04 | IMPROVEMENT OF MULTIPURPOSE HALL & CONCRETING OF PATHWALK WITH CANAL LINING IN BRGY. BENDITA II | 652375 | 030 & 031 | VERTICAL STRUCTURES | IMPROVEMENT
10 | 2025-05-26 | Poblacion 2 | Brgy - 20% DF | Released | POW RELEASED DATE: JUNE 11, 2025 | 2025-12-04 | CONSTRUCTION OF GROUTED RIP-RAP AT ANDA ST. EXTENSION, BRGY. II | 166761.2 | 019 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
11 | 2025-05-26 | Poblacion 2 | Brgy - 20% DF | Released | POW RELEASED DATE: JUNE 11, 2025 | 2025-12-04 | CONSTRUCTION OF CANAL COVER AT REAL ST. & PACHECO ST., BRGY. II | 200000 | 020 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
12 | 2025-05-26 | Poblacion 2 | Brgy - 20% DF | Released | POW RELEASED DATE: JUNE 11, 2025 | 2025-12-04 | IMPROVEMENT / REHABILITATION OF CEILING & ROOFING OF MULTIPURPOSE HALL IN BRGY. II | 100000 | 021 | VERTICAL STRUCTURES | REPAIR / REHAB
13 | 2025-05-27 | Poblacion 4 | Brgy - 20% DF | Released | POW RELEASED DATE: JULY 7, 2025 | 2025-12-04 | IMPROVEMENT OF MULTIPURPOSE HALL IN BRGY. IV | 539239.4 | 028 | VERTICAL STRUCTURES | REPAIR / REHAB
14 | 2025-05-29 | Medina | Brgy - 20% DF | Released | POW RELEASED DATE: JUNE 16 2025 | 2025-12-04 | CONCRETING OF ROAD IN SITIO KAY-IMUS, BRGY MEDINA | 932409 | 022 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
15 | 2025-05-29 | Medina | Brgy - 20% DF | Released | POW RELEASED DATE: JUNE 16 2025 | 2025-12-04 | CONSTRUCTION OF FENCING IN BRGY. MEDINA | 300000 | 023 | VERTICAL STRUCTURES | NEW
16 | 2025-05-29 | Medina | Brgy - 20% DF | Released | RELEASED TO UWENG JUNE 26, 2025 | 2025-12-04 | IMPROVEMENT OF ROAD STEPS IN SITIO KAY-APAS, BRGY. MEDINA | 235912 | 024a | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
17 | 2025-06-03 | San Agustin | Brgy - 20% DF | Released | POW RELEASED DATE: JUNE 19 2025 | 2025-12-04 | CONCRETING OF PATHWALK AT AVOCADO ST., BRGY. SAN AGUSTIN | 150000 | 025 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
18 | 2025-06-03 | San Agustin | Brgy - 20% DF | Released | POW RELEASED DATE: JUNE 19 2025 | 2025-12-04 | CONCRETING OF PATHWALK AT BANABA ST., BRGY. SAN AGUSTIN | 150000 | 026 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
19 | 2025-06-03 | San Agustin | Brgy - 20% DF | Released | POW RELEASED DATE: JUNE 19 2025 | 2025-12-04 | CONCRETING OF PATHWALK AT SAMPALOC ST., BRGY. SAN AGUSTIN | 100000 | 027 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
20 | 2025-06-30 | Caluangan | Brgy - 20% DF | Released | POW RELEASED DATE: AUG 19 2025 | 2025-12-04 | INSTALLATION OF SOLAR STREET LIGHTS | 344400 | 033 | TELECOMMUNICATION / POWER & LIGHT SERVICE | NEW
21 | 2025-06-30 | Caluangan | Brgy - 20% DF | Released | POW RELEASED DATE: AUG 19 2025 | 2025-12-04 | IMPROVEMENT OF DAYCARE CENTER | 204600 | 032 | VERTICAL STRUCTURES | IMPROVEMENT
22 | 2025-07-14 | Baliwag | Brgy - 20% DF | Released | POW RELEASED DATE: SEPT 2 2025 | 2025-12-04 | CONSTRUCTION OF PUROK & STREET SIGNAGES | 254500 | 039 | ADMINISTRATIVE SUPPORT | NEW
23 | 2025-07-16 | Poblacion 5 | Brgy - 20% DF | Released | POW RELEASED DATE: SEPT 3 2025 | 2025-12-04 | CONSTRUCTION OF RECEIVING AREA | 350500 | 045 | VERTICAL STRUCTURES | NEW
24 | 2025-07-16 | Poblacion 5 | Brgy - 20% DF | Released | POW RELEASED DATE: AUG 19 2025 | 2025-12-04 | REPAIR & REHABILITATION OF MULTIPURPOSE HALL | 255000 | 040 | VERTICAL STRUCTURES | IMPROVEMENT
25 | 2025-07-16 | Poblacion 5 | Brgy - 20% DF | Released | POW RELEASED DATE: AUG 19 2025 | 2025-12-04 | CANAL LINING CONCRETE COVER | 100000 | 041 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
26 | 2025-08-04 | Ramirez | Brgy - 20% DF | Released | POW RELEASED DATE: OCT 15 2025 | 2025-12-04 | CANAL LINING AT SITIO KANLURAN | 218979.2 | 067 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
27 | 2025-08-04 | Ramirez | Brgy - 20% DF | Released | POW RELEASED DATE: OCT 15 2025 | 2025-12-04 | CANAL LINING AT SITIO KANLURAN | 242580 | 066 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
28 | 2025-08-04 | Ramirez | Brgy - 20% DF | Released | POW RELEASED DATE: OCT 15 2025 | 2025-12-04 | CANAL LINING AT SITIO SILANGAN | 200000 | 068 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
29 | 2025-08-06 | Urdaneta | Brgy - 20% DF | Released | POW RELEASED DATE: SEPT 9 2025 | 2025-12-04 | REHABILITATION OF MULTIPURPOSE HALL | 300000 | 046 | MULTIPURPOSE BUILDING / CIVIC CENTER | REPAIR / REHAB
30 | 2025-08-06 | Urdaneta | Brgy - 20% DF | Released | POW RELEASED DATE: SEPT 9 2025 | 2025-12-04 | CONSTRUCTION OF CANAL LINING AT SITIO GULOD | 250000 | 047 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
31 | 2025-08-06 | Kabulusan | Brgy - 20% DF | Released | POW RELEASED DATE: SEPT 4 2025 | 2025-12-04 | CANAL LINING AT PUROK 1 & PUROK 3 | 149000 | 044 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
32 | 2025-08-06 | Kabulusan | Brgy - 20% DF | Released | POW RELEASED DATE: SEPT 4 2025 | 2025-12-04 | CONCRETING OF ROAD AT PUROK 3 | 821905 | 043 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
33 | 2025-08-20 | Poblacion 1 | Brgy - 20% DF | Released | POW RELEASED DATE: NOV 21 2025 | 2025-12-04 | INSTALLATION OF HANDLE BARS GOING TO QUIAPO RIVER | 46000 | 065 | VERTICAL STRUCTURES | IMPROVEMENT
34 | 2025-09-08 | Baliwag | Brgy - 20% DF | Released | POW RELEASED DATE: NOV 5 2025 | 2025-12-04 | INSTALLATION OF SOLAR STREET LIGHTS, BRGY. BALIWAG | 468565.8 | 069a | TELECOMMUNICATION / POWER & LIGHT SERVICE | NEW
35 | 2025-09-17 | Tua | Brgy - 20% DF | Released | POW RELEASED DATE: NOV 21 2025 | 2025-12-04 | IMPROVEMENT OF MULTIPURPOSE HALL, BRGY. TUA | 841260 | 070a | VERTICAL STRUCTURES | IMPROVEMENT
36 | 2025-10-10 | Ramirez | Brgy - 20% DF | Released | POW RELEASED DATE: NOV 17 2025 | 2025-12-04 | IMPROVEMENT OF BRGY. RAMIREZ MULTIPURPOSE HALL, | 157420 | 074 | VERTICAL STRUCTURES | IMPROVEMENT
37 | 2025-10-20 | Caluangan | Brgy - 20% DF | Released | POW RELEASED DATE: NOV 5 2025 | 2025-12-04 | CANAL LINING | 200000 | 073 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
38 | 2025-10-20 | Pacheco | Brgy - 20% DF | Released | POW RELEASED DATE: NOV 5 2025 | 2025-12-04 | CANAL LINING | 300000 | 071 | RAINWATER CATCHMENT / CANAL LINING FACILITIES | NEW
39 | 2025-10-20 | Pacheco | Brgy - 20% DF | Released | POW RELEASED DATE: NOV 5 2025 | 2025-12-04 | CONCRETE PATHWALK | 278845 | 072 | LOCAL ROADS & OTHER HORIZONTAL FACILITIES | NEW
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
Formulas:
Last Modified Date = [Last Modified Date, row above]

## DEPEDSEF 2025
Republic of the Philippines
Province of Cavite
MUNICIPALITY OF MAGALLANES
OFFICE OF THE MUNICIPAL ENGINEER
PROGRAM OF WORKS STATUS SUMMARY F.Y. 2025 - SEF FUNDED PROJECTS
2025-12-04
Item | Request Received Date | SCHOOL LEVEL | Project Location | Source of Fund | Status | Remarks / Comments | Last Modified Date | Project Title | Project Amount | POW | Project Type | Type of Construction
1 | 2025-02-26 | Elementary | Ramirez | SEF - 2025 | COMPLETED | COC - JULY 31, 2025 | 2025-12-04 | CONSTRUCTION OF PERIMETER FENCE | 71000 | 008 | VERTICAL STRUCTURES | REPAIR / REHAB
2 | 2025-02-27 | Elementary | Medina | SEF - 2025 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY | 2025-12-04 | REPAIR OF TLE CLASSROOM (MATERIALS) | 49950 | 009 | VERTICAL STRUCTURES | REPAIR / REHAB
3 | 2025-03-06 | Elementary | Magallanes (Pob. 1) | SEF - 2025 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY | 2025-12-04 | REPAIR / MAINTENANCE OF SCHOOL FACILITIES | 259800 |  | VERTICAL STRUCTURES | REPAIR / REHAB
4 | 2025-03-06 | Elementary | Urdaneta | SEF - 2025 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY | 2025-12-04 | CONSTRUCTION OF SEPTIC TANK | 49990 |  | VERTICAL STRUCTURES | NEW
5 | 2025-03-10 | Elementary | Kabulusan | SEF - 2025 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY | 2025-12-04 | CONSTRUCTION OF KITCHEN IN PRINCIPAL'S OFFICE | 49500 | 011 | VERTICAL STRUCTURES | NEW
6 | 2025-03-10 | Elementary | Pacheco | SEF - 2025 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY | 2025-12-04 | TILING OF KITCHEN AREA (MATEIALS) | 25000 | 010 | VERTICAL STRUCTURES | IMPROVEMENT
7 | 2025-03-12 | Elementary | Tua | SEF - 2025 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY | 2025-12-04 | CONSTRUCTION OF WALKWAYS; CANTEEN KITCHEN ROOFING & CEILING REPAIR; CANTEEN SHELVES CONSTRUCTION | 97500 |  | VERTICAL STRUCTURES | REPAIR / REHAB
8 | 2025-03-17 | Elementary | Bendita 1 | SEF - 2025 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY | 2025-12-04 | CONSTRUCTION OF PRINCIPAL'S OFFICE KITCHEN & REPAIR OF ROOFING OF DPWH BUILDING | 127500 |  | VERTICAL STRUCTURES | IMPROVEMENT
9 | 2025-03-20 | Elementary | Caluangan | SEF - 2025 | N /A | POW NOT APPLICABLE FOR MATERIALS ONLY | 2025-12-04 | REPAIR OF COVERED PATHWAY CEILING | 11000 |  | VERTICAL STRUCTURES | REPAIR / REHAB
10 | 2025-04-21 | Elementary | Baliwag | SEF - 2025 | COMPLETED |  | 2025-12-04 | CONSTRUCTION OF PATKWALK SHED | 58500 | 018 | VERTICAL STRUCTURES | NEW
11 | 2025-08-05 | High School | Bendita 2 | SEF - 2025 | FINAL INSPECTION | WITH FINDINGS DEADLINE - OCT 15 2025 (C/O CONTRACTOR) | 2025-12-04 | IMPROVEMENT / REHABILITATION OF FOUR (4) STOREY SCHOOL IN BENDITA | 260100 | 017a | VERTICAL STRUCTURES | IMPROVEMENT
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
2025-12-04
Formulas:
Last Modified Date = [Last Modified Date, row above]